Table of Contents

# Project TODO · Progress Tracker

Project: AI-Driven Investment Intelligence Platform (investment) Roadmap reference: docs/Roadmap.md Convention: [x] done · [~] in progress · [ ] pending · [!] blocked Update this file at the end of every working session.

## At a glance

| Phase | Window | Status | % done |
| --- | --- | --- | --- |
| Docs & UI prototype | 2026-04-22 | ✅ complete | 100% |
| M0 · Foundation (backend scaffolding) | 2026-04-22 → 2026-05-05 | ✅ complete | 100% (Neon live, seed green, auth round-trip green) |
| M1 · Data Layer (real APIs + real ingestion) | 2026-04-23 → 2026-06-02 | ✅ complete | 100% (30+ APIs · cron · all 13 pages live) |
| Phase A · Security hardening | 2026-04-23 | ✅ complete | 100% |
| Step 1 · Scheduler + IngestLog | 2026-04-24 | ✅ complete | Vercel Cron wired for AMFI/NSE/Yahoo |
| Step 2 · Kill the mocks | 2026-04-24 | ✅ complete | All 13 pages on Neon · mocks deleted |
| Phase D v0 · Rule-based signal engine | 2026-04-24 | ✅ complete | Features + signals + regime live · 6.5 s end-to-end |
| Phase E · Reports + PDF + email + forgot-password | 2026-04-24 | ✅ complete | Template reports · PDF · Resend+stub · full reset round-trip |
| Phase F · Alerts evaluator | 2026-04-26 | ✅ complete | 3 rule types · per-day idempotent · UI feed + 30 s polling + bell badge |
| Phase G · Tests + observability + deploy prep | 2026-04-26 | ✅ code-complete | Sentry · Upstash adapter · 56 unit tests · 3 e2e specs · CI matrix · DEPLOY.md · /status |
| Production deploy | TBD | ⏳ ready | Follow docs/DEPLOY.md — ~90 min runbook |
| M2 · Analytics & Signals | 2026-06-03 → 2026-06-30 | ⏳ not started | 0% |
| M3 · Portal & Reports (backend side) | 2026-07-01 → 2026-07-28 | ⏳ not started | 0% |
| M4 · Hardening & Launch | 2026-07-29 → 2026-08-18 | ⏳ not started | 0% |
| M5 · Advanced (optional) | 2026-08-19 → 2026-10-13 | ⏳ not started | 0% |

## ✅ Session 2026-04-22 — Docs & UI prototype (DONE)

Documentation (delivered in .md + .docx)

- Statement of Work (docs/SoW.md, docs/SoW.docx)

- Roadmap (docs/Roadmap.md, docs/Roadmap.docx)

- Developers Guide (docs/Developers-Guide.md, .docx)

- User Manual (docs/User-Manual.md, .docx)

UI scaffolding (Next.js 16 + React 19 dev server on :3000)

- Claude-style design tokens (OKLCH palette, dark mode variant, serif display)

- shadcn-style primitives: Button, Card, Input, Label, Badge, Separator, Table, Tabs, Avatar, Switch, Select, Dialog, MetricTile

- reactbits-style motion: FadeIn, Stagger, GradientBlob, ShinyText, NumberFlow

- App shell — Sidebar (with pinned "For you" primary CTA), Topbar, PageHeader

- Auth: /login, /register with Zustand-persisted auth store

- Landing page / with animated hero + preview card + feature grid

- Dashboard /dashboard — KPI tiles, NIFTY 50 chart, Market Regime, Top BUYs, Allocation, Sector Strength, Avoid list, + "For you" banner

- Assets /assets — filter pills + search + AI-score table

- Asset detail /assets/[symbol] — 5 tabs (Overview, Price, Metrics, Signal History, Corp Actions)

- Compare /compare — up to 4 assets, normalized % chart + metrics matrix

- Signals /signals — grouped tables + Performance ledger

- Reports /reports, /reports/[date] — latest summary + archive + full sectioned view

- Alerts /alerts — interactive table with Switch + delete

- Settings /settings — Profile / Security / Notifications / Appearance (dark mode) / API keys

"For you" — plain-English plan builder (added in same session)

- /for-you route with 3-question wizard (amount, horizon, risk)

- Auto-generated plan: rupee-split across Growth / Safe / Hedge

- Per-pick cards with plain-language rationale, rupee amount, hold duration, confidence %

- Plain-English avoid list

- Plain-English market-regime read

- useUiStore (Zustand + localStorage persist) for amount / horizon / risk

- Prominent sidebar CTA for /for-you + dashboard banner

Folder structure (per SoW §7)

- src/app/ — route handlers + (auth) / (app) groups

- src/frontend/{components,hooks,store,utils}/

- src/shared/{types,mocks,constants}/

- Mock data (15 assets, signal history, corp actions, 3 reports, alerts, regime, sectors)

Smoke test (all 13 routes return 200 with expected content)

- /, /login, /register

- /for-you, /dashboard, /assets, /assets/RELIANCE, /compare, /signals, /reports, /reports/2026-04-22, /alerts, /settings

## 🟡 M0 · Foundation · 2026-04-22 → 2026-05-05

Outcome: real backend, real auth, local Docker environment.

Tooling & infra

- docker-compose.yml for Postgres 16 + Redis 7 + MailHog (MLflow deferred to M2)

- Install dev deps: prisma, @prisma/adapter-pg, @prisma/client, zod, jose, argon2, pino, pino-http, nanoid, @tanstack/react-query, axios

- Package manager decision — we stayed on npm (existing lockfile). Revisit before CI.

- just task runner (deferred — not blocking)

Environment validation

- src/config/env.ts — Zod schema, empty-string → undefined safety for optional vars

- .env.example committed; .env.local bootstrapped from it

- .env.production template (will add during M4 hardening)

Database

- Prisma 7 schema in src/backend/database/prisma/schema.prisma with ALL 14 models (User, RefreshToken, Asset, AssetPrice, MfNav, CorporateAction, FeaturesDaily, SignalsDaily, MarketRegime, Report, Alert, AlertEvent, AuditLog, enums)

- prisma.config.ts (Prisma 7 style — URL lives here, not in schema)

- src/backend/database/client.ts (PrismaPg driver adapter, dev-friendly global cache)

- src/backend/database/seed.ts (demo user demo@investa.local / Demo@123 + assets + today's signals + regime)

- npx prisma generate succeeds (client at node_modules/.prisma/client)

- NeonDB URL pasted, prisma migrate dev --name init → schema live in Neon

- prisma db seed → demo user + 16 assets + today's signals + regime

- Demo user promoted to ADMIN via prisma db execute — /admin/health returns 200 with dbLatencyMs

- Hypertable migration SQL for asset_prices and mf_nav (deferred to M1 when we start ingesting real prices)

Auth

- Zod validators: register, login, forgot-password, reset-password

- Repositories: user.repository.ts, refresh-token.repository.ts

- AuthService — register, login, refresh (with rotation), logout, me

- Middleware: withApi, withAuth, withAdmin — all thread requestId + problem+json

- POST /api/v1/auth/register — smoke 422 works (empty body → structured error)

- POST /api/v1/auth/login

- POST /api/v1/auth/refresh (rotates refresh token)

- POST /api/v1/auth/logout — clears cookies + revokes server-side

- GET /api/v1/auth/me — smoke 401 works (no cookie → "Missing access token")

- HttpOnly / Secure / SameSite cookies via cookies.util.ts

- Frontend: axios client with 401→/auth/refresh→retry-once interceptor

- LoginForm + RegisterForm rewired to real API + Axios error surfacing

- Topbar logout button calls /auth/logout then clears Zustand + redirects

- POST /api/v1/auth/forgot-password + POST /api/v1/auth/reset-password (deferred — needs email service)

FastAPI analytics service skeleton (deferred to M1 start)

- Install Python 3.12 (machine has 3.9.6) and uv

- services/analytics/ with pyproject.toml — FastAPI, SQLAlchemy, Alembic, pandas, numpy

- GET /health (liveness + readiness)

- Internal X-Internal-Key middleware (never exposed to browser)

- Structured logging (structlog) with request IDs

Observability (baseline)

- pino logger with redacted fields

- request-id middleware (req_<nanoid>)

- GET /api/v1/health — public liveness, returns x-request-id

- GET /api/v1/admin/health — admin-gated DB ping (Prisma SELECT 1 + latency)

- /metrics Prometheus endpoint (deferred — comes with hosting in M4)

CI/CD

- .github/workflows/ci.yml — Postgres service, prisma generate, lint, tsc --noEmit, next build on PR

- ESLint custom rule enforcing folder structure (nice-to-have — deferred)

Acceptance gate for M0

- npx tsc --noEmit clean

- Every existing UI route still 200 (13 routes verified)

- /api/v1/health returns 200 JSON

- /api/v1/auth/me (no cookie) returns 401 application/problem+json with x-request-id

- /api/v1/auth/register validation errors return 422 with field-level paths

- Full round-trip against Neon: login → cookie issued → /auth/me returns user → /auth/refresh rotates → /auth/me still works → /auth/logout clears → /auth/me returns 401

- /api/v1/admin/health returns 200 with live dbLatencyMs after promoting demo user to ADMIN

- CI green on main after first PR (workflow exists; run after first push)

## 🟡 M1 · Data Layer · 2026-04-23 → 2026-06-02

Started early. Portal is now reading from Neon instead of mock files.

Read APIs (DB-backed, live)

- GET /api/v1/assets — paginated list with optional ?type= and ?signal= filters

- GET /api/v1/assets/:symbol — single asset + latest signal

- GET /api/v1/signals/top?type=BUY&n=10 — ranked by probability × confidence

- GET /api/v1/regime/current

- Frontend: QueryProvider (TanStack Query) wired into the (app) layout

- Frontend: assetsApi, regimeApi endpoints; /for-you now reads from them with loading/error states and a Retry button

- GET /api/v1/signals/history?symbol=… — per-asset signal log

- GET /api/v1/signals/sector-strength, /avoid-list

- Wire /dashboard, /assets, /assets/[symbol], /compare, /signals to the new endpoints (still on mocks)

"For you" feature enhancements

- SIP / one-time toggle (frequency field in useUiStore, persisted)

- Presets swap between lumpsum (₹10k–₹5L) and SIP (₹1k–₹25k/mo)

- Plan copy morphs: "₹X today" vs "₹X/month for N months" with total committed

- Money bar + pick cards show /mo suffix in SIP mode

- Regime headline now reads live regime from Neon

Sprint 2 — Equities + Indices (ingestion pipeline — NOT STARTED)

- NSE bhavcopy scraper (ETag-aware, fallback to archive)

- BSE EOD parser

- Equity + index master list with sector/industry mapping

- Corporate actions ingest (splits, dividends, bonuses) with price adjustment

- Airflow DAG ingest_equities_eod scheduled 19:30 IST

- TimescaleDB hypertable asset_prices with compression at 90 days

- Great Expectations data-quality suite (row count, null rates, price sanity)

Sprint 3 — MF, ETFs, Commodities, Currency

- AMFI NAVAll.txt daily ingest + MF master with category + benchmark mapping

- ETFs treated as equity-with-MF-style-benchmark

- Gold + Crude via MCX / delayed feed

- USD/INR via RBI reference rates

- Interpolation / missing-data rules documented + implemented

- features_daily table skeleton with idempotent upsert

API wiring (replace mocks)

- /api/v1/assets (paginated, filtered)

- /api/v1/assets/search

- /api/v1/assets/:symbol

- /api/v1/assets/:symbol/history

- /api/v1/assets/:symbol/corporate-actions

- Replace mockAssets.ts usages in the portal with API calls via TanStack Query hooks

Acceptance gate for M1

- 5 consecutive daily pipeline runs green

- Grafana dashboard shows ingestion health

- Any symbol resolvable to ≥ 5 years of EOD history

## ⏳ M2 · Analytics & Signals · 2026-06-03 → 2026-06-30

Sprint 4 — Feature engineering

- Returns (1d/1w/1m + rolling 1Y/3Y/5Y)

- Risk: stdev, Sharpe, Sortino, max drawdown

- Trend: 20/50/100/200 DMA, RSI-14, MACD(12,26,9)

- Relative strength vs benchmark

- Volatility, correlation matrix, sector rotation indicator

- Liquidity score, MF consistency, downside protection, expense-adjusted return

- Feature-store write path (batch + incremental)

Sprint 5 — Models + recommendation

- Baseline Logistic Regression (seed-pinned, reproducible)

- LightGBM primary model + Random Forest ensemble

- Signal classifier BUY / HOLD / AVOID + probability + confidence

- Market regime detector (HMM or rule-based v1)

- Top-N picks + avoid list endpoints

- Allocation suggestion per (risk, horizon) → drives /for-you

- MLflow model registry + weekly retraining DAG

API wiring

- /api/v1/signals/today, /api/v1/signals/:symbol/history

- /api/v1/signals/regime, /api/v1/signals/sector-strength

- /api/v1/signals/top-picks, /api/v1/signals/avoid-list

- /api/v1/recommendations/allocation, /api/v1/recommendations/sector-allocation, /entries, /exits

- Portal: replace mock signal data with these endpoints

Acceptance gate for M2

- /signals/today returns ≥ 50 real assets with rationales

- Offline backtest: top-decile beats NIFTY50 by ≥ 2% p.a. on 2020–2025 window (informational)

## ⏳ M3 · Portal & Reports (backend) · 2026-07-01 → 2026-07-28

Note: UI portal is already built. This milestone hooks it to real data + adds the report engine.

Reports engine

- Report builder Markdown → HTML with all 6 sections

- weasyprint PDF pipeline, S3 storage

- Email digest via SES / Resend (opt-in)

- LLM narration (Anthropic) with prompt caching + daily cost cap

- /api/v1/reports + /:date + /:date/pdf + /email + /regenerate

Alerts

- Alert evaluator job (runs after signals pipeline)

- /api/v1/alerts CRUD + /events

- SSE (or polling) channel for real-time alert events in UI

Portal integration pass

- Wire /dashboard, /assets, /for-you, /signals, /reports, /alerts to real endpoints (remove mock imports)

- Accessibility pass (axe-core, keyboard nav audit)

- Responsive pass (tables → cards < 768 px)

- Loading states + Suspense boundaries per route (loading.tsx)

Acceptance gate for M3

- Daily report published automatically 5 business days in a row

- Lighthouse: Performance ≥ 85, Accessibility ≥ 95 on Dashboard + Asset Detail

## ⏳ M4 · Hardening & Launch · 2026-07-29 → 2026-08-18

- Rate limiting (per-IP + per-user) on public endpoints

- 100% input validation (Zod portal / Pydantic analytics)

- CORS allowlist, CSRF, CSP, HSTS headers

- Secrets via AWS Secrets Manager (no .env in prod)

- RDS daily snapshots, 7-day PITR, one restore drill

- k6 load test (50 concurrent, p95 < 500 ms on hot paths)

- Security audit: Semgrep, Bandit, npm audit, OWASP ZAP baseline

- UAT with stakeholders + punch-list fix

- On-call runbook + first rotation assigned

- Prod deploy (AWS ECS Fargate + RDS + ElastiCache), DNS, TLS, WAF

- Status page + SLO doc

Acceptance gate for M4

- UAT sign-off from product + client sponsor

- Security review clean

- Observability dashboards green for 7 consecutive days

## ⏳ M5 · Advanced · 2026-08-19 → 2026-10-13 (optional)

- Backtesting engine (vectorized, walk-forward splits)

- Strategy simulator (user-defined rules)

- Portfolio what-if simulation (drag-and-drop weights)

- Sentiment pipeline (NewsAPI + transformers) blended into signal probability

- Global macro linkage (US / VIX correlation)

- Custom rule builder (DSL + UI for overrides)

## 🧭 How to use this file

- At the start of a session: read the "At a glance" table + the current phase section to know where we are.

- While working: flip [ ] to [~] on the items you're actively doing.

- At the end of the session: flip [~] to [x] for what's done, leave [~] for partials, add notes under a Session log sub-heading if context matters, and update the percentage in the glance table.

- If blocked: flip to [!] and add a one-liner explaining the block in the Session log.

## 📝 Session log

### 2026-04-22 — UI prototype + "For you" (plain-English plan)

- Delivered all 4 documents in .md and .docx.

- Scaffolded Next.js 16 portal with Claude-style design tokens, shadcn primitives, reactbits motion.

- Built 13 routes against mock data; dev server verified (all 200s).

- Added /for-you — non-financial-user-friendly plan builder (amount + horizon + risk → rupee split + plain-English picks).

- Pinned "For you" as the primary sidebar CTA and added a dashboard banner.

### 2026-04-22 (pm) — M0 · Foundation (backend scaffolding, ~75%)

- Installed backend deps: Prisma 7, jose, argon2, pino, pino-http, nanoid, axios, TanStack Query.

- Added Zod-validated env at src/config/env.ts (treats empty optional strings as unset — Zod 4 footgun fixed).

- Prisma 7 schema with 14 models + enums (users, refresh_tokens, assets, asset_prices, mf_nav, corporate_actions, features_daily, signals_daily, market_regime, reports, alerts, alert_events, audit_log). Prisma client generates cleanly.

- Built backend utils: jwt (jose, HS256), hash (argon2id + sha256 + randomToken), logger (pino), request-id (req_<nanoid>), error handler (RFC 7807 problem+json), cookies.

- Auth service (register / login / refresh with rotation / logout / me) with repositories, validators, middleware (withApi, withAuth, withAdmin).

- Route handlers live at /api/v1/auth/{register,login,refresh,logout,me}, /api/v1/health, /api/v1/admin/health.

- Frontend wired to real auth: axios client with 401→refresh interceptor, LoginForm + RegisterForm now hit the real API and surface server errors cleanly; Topbar logout revokes server-side.

- docker-compose.yml ready for local infra (Docker not installed on this machine yet).

- .github/workflows/ci.yml with Postgres service, prisma generate, typecheck, build.

- Smoke test passing: 13 UI routes + /api/v1/health → 200; /auth/me → 401 problem+json; /auth/register with bad body → 422 with field-level errors; /auth/login reaches Prisma (fails at DB connect — expected, placeholder URL).

- FastAPI analytics service deferred (machine has Python 3.9.6; needs 3.12 + uv install).

- Next session:

  - Paste real NeonDB Postgres URL into .env.local (set it at DATABASE_URL).

  - npx prisma migrate dev --name init → creates the schema in Neon.

  - npx prisma db seed → creates the demo user + assets + today's signals.

  - Verify full register → login → refresh → logout round-trip with cookies.

  - Begin M1 · Data Layer — NSE bhavcopy scraper, asset master, hypertable migrations (or start M0 FastAPI skeleton if Python 3.12 is installed).

### 2026-04-23 — M0 green end-to-end + real-data APIs + SIP toggle

- NeonDB wired (DATABASE_URL in .env.local), JWT secrets rotated from placeholders.

- npx prisma migrate dev --name init ran clean — schema live in Neon (migration file at src/backend/database/prisma/migrations/20260422162902_init/).

- Installed tsx + server-only as devDeps; removed server-only imports from DB-layer files so Prisma seed runs under plain Node (guard still present in middleware.ts, jwt.util.ts, cookies.util.ts).

- npx prisma db seed — demo user (demo@investa.local / Demo@123), 16 assets, today's signals, market regime.

- Verified full auth round-trip against Neon: login issues HttpOnly cookies → /auth/me returns user → /auth/refresh rotates → /auth/logout clears cookies + revokes server-side → /auth/me correctly 401s.

- Promoted demo user to ADMIN via prisma db execute one-liner; /admin/health returns 200 with live dbLatencyMs (≈ 297 ms to Neon from local).

- New REST APIs from Neon (portal layer): /api/v1/assets, /api/v1/assets/:symbol, /api/v1/signals/top, /api/v1/regime/current. All return the Asset DTO shape the UI already uses; fields not yet persisted (price, returns, RSI, etc.) come back as 0 until M2's analytics pipeline fills them.

- Added QueryProvider (TanStack Query) at the (app) layout root; /for-you is now reading from the real APIs with skeleton loading, error card + Retry.

- SIP / one-time: new frequency field in useUiStore, asked as the first question in the plan builder; amount presets swap automatically (₹1k–₹25k/mo vs ₹10k–₹5L). In SIP mode the plan header reads "Invest ₹X/month", rupee cards show /mo, and a summary card shows total commitment over the horizon (12/36/60 months).

- Next session: wire the other pages (/dashboard, /assets, /assets/[symbol], /compare, /signals) to the same endpoints (remove the remaining mock imports), then start the real ingestion pipeline (NSE bhavcopy + AMFI NAV → populate asset_prices, mf_nav, features_daily, signals_daily).